## Sheet1
Epic | User Stories | Acceptance Criteria | Priority | Sprint
Admin | I want to be able to add admin login so that I can access the admin dashboard. | I should be able to log into the admin dashboard when I enter the valid credentials. | Must be | Sprint 1
User | I want to create an account so that I can access personalized learning and track my progress. | So, I want a sign-up page where I can register my details like username, email, and password. Once submitted, my account should be created. | Must be | Sprint 1
User | I want to log in to my account with my registered email and password so that I can access all system features. | I should be able to log into the website when I enter my username and password on the login page. I should now be able to explore the features of the system. | Must be | Sprint 1
User | I want to log out of my account so that my session remains secure. | When I click on the logout button, my session should expire and I should be redirected to the login page. | Must be | Sprint 1
User | I want to reset my password so that if I forget it, I can still access my account. | Given that I click on "Forgot Password," I should see a form to enter my registered email, and then I should be able to set a new password through an email link. | Should be | Sprint 2
User | I want to sign up using social media platforms like Google and Facebook so that I can register quickly. | When I click on the Google, Instagram, or Facebook sign-up option. I should be able to log in or register using my social media account. | Could be | Sprint 2
Admin | I want to create and manage lessons and quizzes so that users can access updated content. | I should be able to create, update, delete, and manage lessons and quizzes in the system. | Must be | Sprint 2
User | I want to choose which topic to learn (e.g., Intro to Computers, Frontend programming, Backend programming). | Given that I log in, I should see a list of available courses (Intro to Computers, Frontend Development, Backend Development) and be able to select one to proceed. | Must be | Sprint 2
User | I want to input my knowledge level (e.g., Beginner, Basic Knowledge, Computer Student, Professional) so that the system personalizes my learning journey. | I should see an option to choose my knowledge level so that the system should adapt the lessons to my level. | Must be | Sprint 2
User | I want to be able to view the homepage with dashboard and overview of lessons. | When I visit the homepage, I should be able to view the dashboard for navigation and lessons that can be taken. | Must be | Sprint 3
User | I want a button so that I can easily switch the courses. | I want to be able to switch the courses easily. | Should be | Sprint 3
User | I want to open a lesson and view its content so that I can learn the material. | I should be able to view its content, including text, images, and other media as required. | Must be | Sprint 3
User | I want to take quizzes after lessons so that I can test my understanding. | Given that I complete a lesson, I should be able to access a quiz with multiple-choice and fill-in-the-blank questions related to the lesson. | Must be | Sprint 3
User | I want to receive real-time feedback on my quiz answers so that I can learn from my mistakes. | I should be able to see instant feedback on whether it was correct or incorrect. If the answer is incorrect, it should explain the correct answer. | Must be | Sprint 3
User | I wish to take quizzes again which I initially failed in order to advance my scores. | Given that I failed the quiz, I should receive another chance to take a quiz when revisiting the feedback from prior attempts. | Should be | Sprint 3
Admin | I want to manage badges and points for users so that gamification can enhance user engagement. | As an admin, I should be able to create, update, and assign badges and point thresholds for specific achievements or completion of daily quests in the system. | Must be | Sprint 4
Admin | I want to configure leaderboard settings so that I can adjust the criteria for ranking users according to their points accumulation. | I should be able to set up leaderboard parameters, such as points, badges, or quiz performance metrics. | Should be | Sprint 4
User | I want to see my learning progress as a dashboard for self-monitoring my educational advancement. | The dashboard must display quiz scores and completed lessons together with earned badges when I log in. | Must be | Sprint 4
User | A motivational system of points and badges that reward should be provided when I successfully complete lessons and quizzes. | When I reach specified achievement points, these developments should appear on my dashboard for monitoring. | Must be | Sprint 4
User | I want to view a leaderboard so that I can spark my competitive spirit. | I should be able to visit a leaderboard displaying the top leader based on points or badge along with my own rank. | Should be | Sprint 4
Admin | I want to utilize email marketing tools for reaching out to users in order to boost their involvement. | I should be able to distribute email campaigns directed at non-active users and upcoming lesson notifications to the users. | Must be | Sprint 4
User | I want to receive notifications about new lessons and pending quizzes so that I stay engaged. | I should receive in-app or email notifications when new lessons are added or when I have pending quizzes. | Must be | Sprint 4